## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to Project (Log Analytics Monitoring Engine) and milestone planning | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S2 | S2 | US-001 | Understanding Python, Libraries, API, Backend, Frontend, Web Technologies, Dask, Config Files | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S3 | S3 | US-001 | Dask Basics, Cluster Setup, Data Manipulation, Virtual Environment | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S4 | S4 | US-001 | Skillr Website Overview & Virtual Environment Management | SHOULD HAVE | Skillr Platform | Gogula Avinash Kumar | 3- Completed
S5 | S5 | US-001 | Installing Dask (pip install dask[complete]) | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S6 | S6 | US-001 | Creating main and dask config & Connecting to Dask | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S7 | S7 | US-001 | Creating Log Schema (schema design & parser concept) | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S8 | S8 | US-001 | Developing parser & Regex Implementation | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S9 | S9 | US-001 | Explained parser code, regex, and timestamp conversion. | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S10 | S10 | US-001 | Milestone 1 Completion | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S11 | S11 | US-001 | Introduction to Python Ray | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S12 | S12 | US-001 | Project Review & Feedback Collection | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S13 | S13 | US-001 | Milestone 2 Planning & Review Discussion | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S14 | S14 | US-001 | Updating Milestone 1 and Creating Data Pipeline to Convert Logs into Dask Bag | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S15 | S15 | US-001 | About JSON, Updates in processing and main file and Milestone 2 Completion | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S16 | S16 | US-001 | Project, Sprint & Document Review; Introduction to Milestone-3; Anomaly Detection and Alerting Concepts | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S17 | S17 | US-001 | Project and Document Review; Anomaly Detection Types (Statistical, ML, Rule-based) and Alerting Concepts | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S18 | S18 | US-001 | Understanding Port Numbers and Their Uses; Email Configuration Code for Alert Notifications | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S-19 | S-19 | US-001 | Discussed about Standard Deviation and Z-score | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S-20 | S-20 | US-001 | Anomaly Detection Code | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S-21 | S-21 | US-001 | Explanation for anomaly detection code | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S-22 | S-22 | US-001 | Project, Sprint, and Document Review; discussed how the final presentation will be conducted. | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S-23 | S-23 | US-001 | Discussed the functionality and implementation | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S-24 | S-24 | US-001 | Discussed generating and collecting log data | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S-25 | S-25 | US-001 | Discussed about Streamlit and its uses | SHOULD HAVE | Streamlit | Gogula Avinash Kumar | 3- Completed
S-26 | S-26 | US-001 | Discussed Streamlit components and Plotly | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S-27 | S-27 | US-001 | Corrected errors in the code and worked on the Streamlit dashboard. | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S-28 | S-28 | US-001 | Added MIT License to the project and discussed the PPT creation for the final presentation. | MUST HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
S-29 | S-29 | US-001 | Fixed errors in the code. | SHOULD HAVE | No Dependency | Gogula Avinash Kumar | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7